## Sheet1
| User Story Completed | Predicted Hours | Actual Hours | General Comments | User Comments | Developer Comments
Sprint 1 Week 1 | SI1 | 6 | 4 |  | Make the website pretty and standout more. Clean layout with a header bar with menu options
Will work on layout more next week working on functionality first
Sprint 1 Week 2 | SI1 | 6 | 10 | (working on website layout)
Users information their Gender option should also include an other part incase they do not identify as male or female
Sprint 1 Week 3 | SI2 | 5 | 8 | (took a lot longer) |  | This can be easily implemted to accomodate the site
Sprint 1 Week 4 | SI3 | 4 | 4 |  | Not all said users stories were completed why?
Due to the loss of the main developer this had set back the first sprint we hope to increase velocity in the second
Sprint 2 Week 1 | SI8 | 6 | 2 | Could view through native Django | Okay please ensure this is completed in the next sprint (SI5)
| SI13 | N/A | 2 | Aided by Django
| SI7 | 12 | 10
User needs an option to select between teacher and student
Sprint 2 Week 2 | SI12 | N/A | 2 |  |  | will add a radio button for this choice
Sprit 2 Week 3 | SI5 | 19 | 20 |  |  | user story 17 and 20 were merged as this was easier for the user
login is taking longer to develop than previously thought
we are rationlising the functionality of instrument over the login preference